**Project Status Report**

|  |  |  |  |
| --- | --- | --- | --- |
| Project Name: | Study Cache ( Studdee ) | | |
| Team Members: | Adam Wiethuechter, Ben Foster, Mat Utter, Roman Pendrar | | |
| Date: | 10/9/2013 | Cycle Number: | 3 |

|  |  |
| --- | --- |
| System Intent: | Create a website for making studying better by delivering documents with other content to users in a good way. |

|  |  |
| --- | --- |
| Cycle Intent: | Move development to windows platforms and move project management to Github. Remake the upload feature to support out specific needs. Create a working DocView feature, user interface |

Accomplishments since the last status report:

* Successfully moved development to windows hosts
* Created working testable versions of the following,
  + login,
  + upload
  + browse
  + docview
  + rating system

Obstacles encountered since the last status report:

* portability to unix from windows, directory access needs \ in unix and / in windows, code was modified so only one character need be changed

Risks facing the project:

* Time management

Objectives for the next week:

* Refine the look/functionality of the UI (css stuff)
* Make the search bar feature
* Make the workbook feature
* Make the profile feature

User Features:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Planned | | | Actual | | |
| # | User Feature <***Short Name: Short Description***> | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status  (completed, discarded, in progress, unstarted, etc.) | Actual hours this cycle | Total actual hours this project |
| 1 | Document View<docview:the front end interface for viewing partial document and user comments> | 2 | 16 | 8 | complete | 1 | 10 |
| 2 | Search Result<searchview:the front end that presents results from a search query> | 3 | 24 | 8 | In progress | 1 | 9 |
| 3 | Search bar <searchbar: navigation bar and search form at the top of every page | 3 | 20 | 8 | In progress | 2 | 17 |
| 4 | Side bar <sidebar: useful information available on the side of every page | 3 | 4 | 8 | In progress | 0 | 4 |
| 5 | Database <DB: includes relations and methods for storing and collecting documents and uploaded data | Perpetual |  | 8 | Technical issue | 0 | 0 |
| 6 | Search Form <searchform: more detailed and flexible search form> | 2 | 12 | 8 | In progress | 2 | 2 |
| 7 | Admin Page <adminpage: administrative page> | 3 | 10 | 8 | In progress | 3 | 3 |
| 8 | Upload Form <uploadform: form to upload content> | 2 | 16 | 8 | complete | 6 | 6 |
| 9 | Rating system | 3 | 8 | 0 | complete | 2 | 8 |
| 10 | Login | 3 | 6 | 0 | complete | 0 | 6 |
| 11 | browse | 3 | 2 | 2 | complete | 2 | 2 |

Team Actions:

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | User Feature <***# only***> | | | Planned | Actual | | | | | | | |
| Name | Coder | Tester(s) | Reviewer(s) | Planned hours this cycle | Process hours | | Product hours | | Customer hours | | Total hours | |
| Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle |
| Adam Wiethuechter | 1,8 | 8,9,10,11 | 8,9,10,11 | 18 | 3 | 3 | 5 | 5 |  |  | 8 | 8 |
| Ben Foster | 5,8 | 8,9,10,11 | 8,9 | 12 | 4 | 4 | 2 | 2 |  |  | 6 | 6 |
| Mat Utter | all |  |  | 46 | 2 | 2 | 6 | 6 |  |  | 8 | 8 |
| Roman Pendrar | 1,8 | 8,9,10,11 | 8,9,10,11 | 12 | 3 | 3 | 3 | 3 |  |  | 6 | 6 |